Annual plan

Shay & Gon Erez

2015-2016

Our goals:

* To build personal relationship with the Jewish Community of Youngstown.
* Enhance the connection to Israel, through our eyes.
* Reach out to all kinds of Jews in the Community because of the importance of “Am Israel”
* To play an important role in Hasbara.
* To serve as a reference for any person who wants information about programs in Israel or making ALIYA.
* Connect the community to Israel through Collaboration with the temples.
* To help maintain Jewish life through the connection to Israel
* To share Israel’s history, culture and religion.

September:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by… | Target Audience | Level of Success | Initiator |
| 09.21.15 | Lunch and Learn: “Hafrasht chala”-  time to ask for wishes for the new year | Educate people about one of the most important Jewish mitzvahs | PowerPoint  Food oven (?)  Products needed | The entire community |  | Erez |
| “Hafrasht chala”-  in heritage manor | heritage manor |  |
|  | “Rosh Hashana” Holidays activities in the pre- school | Educate the young kids about the Jewish holidays | Products needed | Pre- school |  | Erez+ Mililani |
| 09.12.15 | Dvar Torah | Preaching to community |  | Ohev-Tzedek |  |  |
| 09.17.15 | 1st Presentation at Boardman Middle School | Connect Israel to non-Jews | Presentation power point. | Non-Jews Teens |  | Erez+ Lori Szoke |
| 09.27.15 | Sukkah Decorating | Decoration a Sukkah at Temples |  | MSJS- El Emeth, Rodef Shalom |  | Akiva |
| 09.27.15 | Hebrew Songs at Erev Sukkot | Learning and singing Hebrew song | Song book+ Guitar Player |  |  |  |

Monthly updates:

Chariot + Web side+ Facebook – high holidays of Tishri. Change for each holiday

Write an article in the JJMM: Patricia interviewed us.

Shlichim Board: Who are the new Shlichim?

October:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by… | Target Audience | Level of Success | Initiator |
| 10.14.15 | teens who came back from Israel-  Meeting #1 | Strengthening the connection of teens which visited Israel with Judaism and Israel. | Budget for bowling and food | teen |  | Erez+ Emily |
|  | Sukkot activities in the pre- school | Educate the young kids about sukkot | Products needed | Pre- school |  | Erez+ Melelani |
| 10.25.15 | Mitzvah day | Taking part in our “mitzvah day” of Sunday school |  | Sunday school |  | Akiva+ MSJS |

Monthly updates:

Chariot: sukkot and Simhat Tora & Yitzhak Rabin Memorial Day.

Write an article in the JJMM: Article about Tishrei Holidays

Shlichim board: What’s new in Israel?

November:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by… | Target Audience | Level of Success | | Initiator |
| 11.05.15 | PJ Library- Challah Tots | Educate kids about Challah | - | Jewish young kids |  | | Emily |
| 11.06.15 | L&L-  Mohammad Darawshe, Director of Planning, Equality & Shared Society. Inter-Agency Task Force on Israeli Arab Issues | Learning about Arab-Jewish relations in Israel | Advertising | Jewish and Muslim community |  | | Erez+ Debbie |
| 11.09.15 | Young Adult evening | Meet each other and having fun |  | Young Adult |  | | Erez |
| 11.07.15 | Lecture about Israel in El Emet | Teach about Israel |  | Jewish community |  | | Erez |
| 11.24.15 | Yotam Polizer  Psycho-Social Program Coordinator  *Asia Regional Director.* IsraAid | Teach about Israel Humanitarian activities world wide | Dinner\Lunch | Jewish community and wide community+  YSU |  | | Erez+ Helene |
| 11.10.15 | 2nd Presentation at Boardman Middle School | Connect Israel to non-Jews | Presentation power point. | Non-Jews Teens | |  | Erez+ Lori Szoke |
| 11.12.15 | Rosh Chodesh meeting- Shai’s lecture | Teach about the portion |  | Rosh Chodesh in El Emet | |  | Erez |
| 11.30.15 | Chanukah Party in El- Emet | Bring some Israeliness into the temples | Practice the dance and prepare the playlist | The Temples | |  | Rabbis+  Erez |
| 11.30.15 | Challah program in Levy Garden | Educate people about Challah | Ingredients | Levy Garden residences | |  | Erez+ Rona |

Monthly updates:

Chariot: Israel as a rainbow of cultures and Traditions

Write an article in the JJMM: An article about Itzchak Rabin

Shlichim board: News update

December:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
| 12.02.15 | PJ Library Channukah Party | Educate Jewish kids about Chanukah |  | Jewish young kids |  | Emily |
| 12.06.15 | Chanukah Candle Lighting at Levy Garden | Educate seniors about Chanukah |  | Levy Garden |  | Levy Garden |
| 12.06.15 | MSJS Chanukah Program | Educate Jewish kids about Chanukah |  | MSJS kids& Parents |  | Tirza |
| 12.07.15 | Chanukah activities in the pre- school | Educate the young kids about Hanukah | Products needed | Pre- school |  | Erez+ Jenn |
| 12.09.15 | Chanukah Candle Lighting at Heritage Manor | Educate seniors about Chanukah |  | Heritage Manor |  | Heritage Manor |
| 12.10.15 | Akiva Hanukkah party. | HANUKKA MESHUGANESS | Choregraphy and dance | The Community |  | Akiva |
| 12.11.15 | Chanukah Party in Rodef Shalom | Bring some Israeliness into the temples | Practice the dance and prepare the playlist | The Temples |  | Rabbis+  Erez |

Write an article in the JJMM: send by December 19th

Chariot: Chanukka

January:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
|  | Tu B’Shvat Holiday activities in the pre- school |  | Decorations on plates with Fruits and Vegetables  AND  Little package to take home | CDC |  | Erez+ Jenn |
| 01.07.16 | Concept Night  Ethiopian Night  Israel as a rainbow of cultures and Traditions | Taste of Israel multiculturalis | Food  Maintenance  Decorations PowerPoint | The community |  | Erez |
| 01.20.16 | PJ Library Tu bishvat Party | Educate Jewish kids about Tu beshvat |  | Jewish young kids |  | Emily |
| 01.23.16 | Tu bishvat Party in El Emet | Bring some Israeliness into the temples | Practice the dance and prepare the playlist | The Temples |  | Rabbis+  Erez |
| 01.24.16 | Generation to Generation program (No. 1) | Contact between young and The senior in the community |  | Jewish kids+ Levy Garden seniors |  | Erez+ Emily+ Tirtza+ Ronna |

Monthly updates:

Write an article in the JJMM: send by December 19th

Chariot: Israel Humanitarian Intervention in the world

February:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
| 02.03.16 | Lunch & Learn- Maayana Beranigan | Learning about the story of Maayana that made Alya from the virgin Islands. |  |  |  |  |
| 02.04.16 | Young Adults get together – Cooking class | Meet each other and having fun |  | Jewish Young Adult |  |  |
| 02.07.16 | Generation to Generation program (No. 2) | Contact between young and The senior in the community |  | Jewish kids+ Levy Garden seniors |  | Erez+ Emily+ Tirtza+ Ronna |
|  | 3rd Presentation at Boardman Middle School | Connect Israel to non-Jews | Presentation power point. | Non-Jews Teens |  | Erez+ Lori Szoke |

Monthly updates:

Write an article in the JJMM: send by January 16th

Write an article in the JJMM: send by February 20th

Chariot: Jews in the Diaspora

March:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
| 03.02.16 | Israeli Concept Night --"Chopped" | Bring some Israeliness into the community | Food  Maintenance  Decorations PowerPoint | All the cummunity |  | Erez |
| 03.10.16 | Girls art night | Meet each other and having fun |  | Jewish Young Adult |  | Erez |
| 03.13.16 | Generation to Generation program (No. 3) | Contact between young and The senior in the community |  | Jewish kids+ Levy Garden seniors |  | Erez+ Emily+ Tirtza+ Ronna |
| 03.16.16 | PJ Library Purim | Educate Jewish kids about Purim |  | Jewish young kids |  | Emily |
| 03.18.16 | Lunch & learn: Randy Goldberg | Learning about Kishinev pogrom |  | Community |  | Erez |
| 03.20.16 | Purim Carnaval | Educate the kids about the Purim |  | The community |  | Akiva+ JCC |
| 03.22.16 | Purim Holiday activities in Akiva | Educate the kids about the Purim |  | Akiva |  | Tirtza |
| 03.23.16 | Purim Holiday activities in the pre- school | Educate the young kids about the Jewish holidays | Products needed | Pre- school |  | Erez+ Mililani |
| 03.23.16 | Purim Holiday activities in El-AMETH | Educate the young kids about the Jewish holidays |  |  |  | EL-AMETH+OHEV TZEDEK |
| 03.28.15 | Goldie Monson- Art Gallery | Bring some Israeliness into the community |  | Community |  | Erez |
| 03.31.15 | Boys night | Meet each other and having fun |  | Jewish Young Adult |  | Erez |

Monthly updates

Write an article in the JJMM: send by March 7th

Chariot:

April:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
| 04.04.16 | Dalia Fadida lecture | Learning about Arab-Jewish relations in Israel | Advertising | Jewish and Muslim community |  | Erez+ Debbie |
| 04.07.16 | Rosh Chodesh meeting- Shai’s lecture | Teach about the portion |  | Rosh Chodesh in El Emet |  | Erez |
| 04.08.16 | Community Shabbat | Educate Jewish kids about Shabbat |  | MSJS+Akiva |  | Erez |
| 04.10.16 | BBYO activity | Connect between Youngstown kids and Cleveland kids |  | Teens |  | Emily |
| 04.14.16 | Akiva model seder | Passover |  | Akiva |  | Tirtza |
| 04.15.16 | Passover Holiday activities in the pre- school | Educate the young kids about the Jewish holidays | Products needed | Pre- school |  | Erez+ Mililani |
| 04.716 | MSJS model seder | Passover |  | Akiva |  | Tirtza |
| 04.18.16 | Lunch & learn: Nimrod Erez | Learning about Yom Kipur war | Music  Pictures  food | Community |  | Erez |
| 04.20.16 | PJ Passover | Educate Jewish kids about Passover |  | Jewish young kids |  | Emily |

May:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
| 05.16.16 | Yom Haatzm’aut party | Connect Israel to Jews non-Jews |  | All community |  | Erez |
| 05.18.16 | Yom Haatzm’aut party (Temple) | Connect Israel to Jewish kids |  |  |  | El- AMETH |
| 05.22.16 | Lag Ba’omer Campfire | Meet each other and having fun study about the holiday | Budget for BBQ, fire etc. | Young Adults with families |  |  |
|  | 4th Presentation at Boardman Middle School | Connect Israel to non-Jews | Presentation power point. | Non-Jews Teens |  | Erez+ Lori Szoke |

Monthly updates:

Write an article in the JJMM: Send by May 2nd

Chariot: Wars of Israel

June:

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Date | Event | Goal | Things that need to be ready by | Target Audience | Level of Success | Initiator |
|  | Shavuot holiday Pre-School | Educate the young kids about the Jewish holidays | Products needed | Pre- school |  | Erez+ Mililani |
|  | Shavuot activity (cooking class???) | Educate the community about the holiday | All community |  |  | Erez |
|  |  |  |  |  |  |  |

Other programs:  
  
\*Private cooking class for the community (15$ for patriciate)  
\* Private lecture about Israel for the community